## 1 - 4 ayland
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
525265 | 454742 | Two Rivers Repairs | Damp and Mould URGENT | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2024-10-25 13:14 | 2024-11-19 12:14 | Photos: Please take before wash photos and after wash photos and attach them to diary notes. Surfaces:Prepare, wash down with RLT Bactdet solution, apply one coat RLT Halophen solution to walls or ceilings in accordance with manufacturers technical data sheet. | Please only look at flats 1&3 Leaseholder called to say there was a problem with the windows please investigate any issues and the wind can be felt through the windows. No notes from previous inspection. | 2024-09-10 14:38 | Specialist Works | Damp and Mould | Cail Lloyd | 70.8 | 70.8 | 14.16 | BLOCK
526529 | 454742 | Two Rivers Repairs | R - Routine | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2024-11-19 10:15 | 2024-11-19 12:14 | Window:Overhaul any type of PVCu window, dismantle as necessary and subsequently reassemble including freeing, easing and adjusting casements to give correct operation, renew fixing screws, remove, refit or renew ironmongery as necessary, check, lubricate operating mechanism, renew gaskets, make good and test. |  | 2024-09-10 14:38 | Carpentry | Responsive | Cail Lloyd | 122.87 | 122.87 | 24.58 | BLOCK
529393 | 454742 | Two Rivers Repairs | R - Routine | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2024-12-16 08:10 | 2025-01-22 15:08 | Double Glazed Unit:Reglaze unit upto 1.00sm, hermetically sealed with 4mm clear float low emissivity (Low E) glass flush edge unit, including remove beads etc. and set aside, hack out glass and glaze new unit to wood, metal or PVCu frames, touch up decoration as necessary to match existing and remove waste and debris. |  | 2024-09-10 14:38 | Glaziers | Responsive | Cail Lloyd | 207.14 | 207.14 | 41.43 | BLOCK
526530 | 454742 | Two Rivers Repairs | R - Routine | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2024-11-19 09:16 | 2024-11-19 12:14 | Vacuum Glazed Unit:Reglaze existing single glazed pane upto 1.00sm, with double glazed clear unit, including remove beads etc. and set aside, hack out glass and glaze new unit to wood, metal or PVCu frames, touch up decoration as necessary to match existing and remove waste and debris. |  | 2024-09-10 14:38 | Glaziers | Responsive | Cail Lloyd | 341.34 | 341.34 | 68.27 | BLOCK
[16 empty] | 742.15 | 148.44
[17 empty] | 890.59 | 222.6475 | cost each

## 13 - 16 ayland
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
518093 | 450676 | Two Rivers Repairs | R - Routine | 7788 | FLATS 13 TO 16, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2024-06-26 15:37 | 2024-06-26 22:33 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Downpipe at the front of the block has come apart at the top. Whilst there please also check the cable from the aerial which is hanging to see if that needs to be tacked back up anywhere (and if poss do that) | 2024-06-20 16:32 | Plumbing | Responsive | Cail Lloyd | 33.29 | 33.29 | 6.66 | BLOCK
39.95
[17 empty] | cost each | 9.9875

## glebe road
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
523616 | 454812 | Midlands Building & Maintenance Limited | R - Routine | 7791 | FLATS 79 TO 93, GLEBE ROAD, NEWENT, GLOUCESTERSHIRE | GL18 1BN | 2024-09-11 11:42 | 2024-10-01 14:51 | We wish to accept your quotation to scaffold (already erected), remove chiminey and make good for the sum of £2435.23 p;us vat | We wish to accept your quotation to scaffold (already erected), remove chiminey and make good for the sum of £2435.23 p;us vat | 2024-09-11 11:42 |  | Responsive | Cail Lloyd | 2526.11 | 2526.11 | 505.22 | BLOCK
Price capped at £250.00 each

## 30 32 harrison way
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
519693 | 451918 | Two Rivers Repairs | R - Routine | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-07-18 13:46 | 2024-07-18 16:25 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | communal light not working entrance | 2024-07-16 13:51 | Electrical | Responsive | Pete Marks | 25.11 | 25.11 | 5.02 | BLOCK
538415 | 466243 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-03-17 08:59 | 2025-03-17 09:13 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-03-17 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
536750 | 464975 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-02-24 15:53 | 2025-02-24 16:35 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-02-21 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
534893 | 463600 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-01-30 15:22 | 2025-01-30 15:39 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-01-30 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
532281 | 461504 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-01-06 12:52 | 2025-01-06 13:03 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-12-30 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
530751 | 460272 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-12-06 12:45 | 2024-12-06 12:58 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-12-05 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
528571 | 458540 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-11-12 08:43 | 2024-11-12 09:14 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-11-11 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
526719 | 457169 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-10-18 12:16 | 2024-10-18 12:19 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-10-17 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
523916 | 455010 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-09-24 15:35 | 2024-09-24 15:55 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-09-16 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
522085 | 453694 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-08-23 12:00 | 2024-08-23 12:07 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-08-23 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
520408 | 452437 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-07-30 09:35 | 2024-07-30 09:56 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-07-29 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
518823 | 451263 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-07-05 13:16 | 2024-07-05 13:35 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-07-04 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
517315 | 450056 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-06-11 14:50 | 2024-06-11 15:05 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-06-08 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
515624 | 448810 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-05-15 12:09 | 2024-05-15 12:19 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-05-11 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
513390 | 447404 | Two Rivers Repairs | 7 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-04-18 13:25 | 2024-04-18 13:40 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-04-14 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
513950 | 447783 | Hygiene Services | R - Routine | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-04-19 15:46 | 2024-04-19 16:06 | drain keeps blocking out back (Manhole) can you take a look when in area next please | drain keeps blocking out back (Manhole) can you take a look when in area next please | 2024-04-19 15:46 |  | Responsive | Pete Marks | 80 | 80 | 16 | BLOCK
513416 | 447430 | Two Rivers Repairs | 60 Days (All Days) | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-05-16 09:45 | 2024-05-16 10:08 | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of RCD's and RCBO's, disconnect, repair and renew and make good as necessary after removal of illegal wiring and components and provide report and test certificate in conformity to BS 7671 to the Client Representative and remove waste and debris. (Code C1 and C2 repairs indentified to be undertaken will be ordered separately by the Client's Representative and will be reimbursed at the relevant rates in this Schedule of Rates). | Lydney - Complete Electrical Installation Condition Report | 2024-04-13 | Electrical | Compliance | Pete Marks | 137.39 | 137.39 | 27.48 | BLOCK
533392 | 462458 | Two Rivers Repairs | U - Urgent | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-01-14 14:50 | 2025-01-14 15:03 | Carbon Monoxide Detector:Isolate, supply and install AICO mains operated carbon monoxide detector including make all necessary connections to supply and make good on completion and remove waste and debris. | Please fit CO detector in ground floor lobby by Gas Meters | 2025-01-13 10:09 | Electrical | Responsive | Pete Marks | 153.57 | 153.57 | 30.71 | BLOCK
526339 | 456866 | A & E Fire and Security | Planned Maintenance | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2024-08-30 16:35 | 2024-08-30 16:35 | A&E Retrospective Invoice - FRA actioned Aug / Sept'24 | A&E Retrospective Invoice - FRA actioned Aug / Sept'24 | 2024-08-30 16:34 |  | Planned Maintenance | Pete Marks | 200 | 200 | 40 | BLOCK
[16 empty] | 1037.49 | 207.55
1245.04
[16 empty] | each | 311.26
535442 | 463995 | FireRite | Planned Maintenance | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-03-31 15:10 | 2025-03-31 15:10 | As per quotation 10278 please can you carry out the FRA works boarding to the door. | As per quotation 10278 please can you carry out the FRA works boarding to the door. | 2025-02-05 16:25 |  | Planned Maintenance | Pete Marks | 3053.76 | 3053.76 | 610.75 | BLOCK
charge capped at £250.00
[15 empty] | each for year |  | 561.26

## 58 to 72 harrison
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
538427 | 466251 | Two Rivers Repairs | R - Routine | 7760 | FLATS 58 TO 72, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BH | 2025-03-19 13:39 | 2025-03-19 14:05 | Client Inspection:Undertake client inspection and testing etc. in connection with fencing and report to Client Representative (any repairs required to be ordered must be instructed by Client Representative). | Fence post was loose but someone's now taken it out of the ground and it's led on the floor of our garden | 2025-03-17 08:41 | Fencing | Responsive | Pete Marks | 17.72 | 17.72 | 3.54 | BLOCK
21.26
[15 empty] | each | 2.6575

## jubilee place
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
523855 | 454972 | Two Rivers Repairs | U - Urgent | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-09-17 14:46 | 2024-09-17 14:46 | as per Kath the drains overflow pipes by the front door dont drain to anything goes onto the ground and collects | as per Kath the drains overflow pipes by the front door dont drain to anything goes onto the ground and collects. if the pipes are owned by no 31 please let us know as the flat is private | 2024-09-13 11:22 | Drainage | Responsive | Cail Lloyd | 29.5 | 29.5 | 5.9 | BLOCK
538271 | 466125 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-03-17 09:09 | 2025-03-17 09:19 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2025-03-13 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
536063 | 464462 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-02-20 10:31 | 2025-02-20 10:34 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2025-02-13 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
533333 | 462414 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-01-20 15:42 | 2025-01-20 15:45 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2025-01-11 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
531391 | 460785 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-12-18 16:07 | 2024-12-18 16:26 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-12-12 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
529168 | 458968 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-11-19 16:11 | 2024-11-19 16:29 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-11-16 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
526080 | 456672 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-10-23 08:10 | 2024-10-23 08:15 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-10-10 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
523926 | 455020 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-09-17 14:25 | 2024-09-17 14:38 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-09-16 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
521977 | 453610 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-08-23 15:33 | 2024-08-23 15:53 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-08-22 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
520421 | 452450 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-07-29 15:09 | 2024-07-29 15:59 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-07-27 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
518479 | 450997 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-07-03 10:36 | 2024-07-03 10:58 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-06-28 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
516920 | 449770 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-06-05 16:01 | 2024-06-05 16:28 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-06-01 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
514526 | 448121 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-05-08 15:03 | 2024-05-08 15:09 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-04-28 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
512278 | 446629 | Two Rivers Repairs | 7 Days (All Days) | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-04-05 10:16 | 2024-04-05 10:51 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 2024-03-31 | Electrical | Compliance | Cail Lloyd | 31.53 | 31.53 | 6.31 | BLOCK
527594 | 457825 | Two Rivers Repairs | R - Routine | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-10-30 09:10 | 2024-10-30 09:40 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | one door is a fire door with a lock so tenants cant access nor postman so block isnt secure. there is a peice of batton which is causing a trip hazard. could just need a step sign | 2024-10-28 10:15 | Carpentry | Responsive | Cail Lloyd | 76.6 | 76.61 | 15.32 | BLOCK
539164 | 466770 | Davies Carpentry & Fire Protection Ltd | 2 Weeks | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS |  |  | Wall around doorset requires repairing Flat 25 | Wall around doorset requires repairing Flat 25 | 2025-03-26 11:13 |  | Please Select | Cail Lloyd | 0 | 120 | 24 | BLOCK
528008 | 458137 | Two Rivers Repairs | E - Daytime Emergency | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2024-11-01 13:37 | 2024-11-01 13:50 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Detector is beeping in the communal stairway, please can we attend. | 2024-11-01 12:12 | Electrical | Responsive | Cail Lloyd | 345.15 | 345.15 | 69.03 | BLOCK
[16 empty] | 981.15 | 196.28
1177.43
[15 empty] | cost each | 147.1787

## Leaze Court
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
518149 | 450720 | Two Rivers Repairs | E - Daytime Emergency | 3179 | LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2024-06-21 15:39 | 2024-06-21 16:07 | Client Inspection:Undertake client inspection and testing etc. in connection with groundworks and report to Client Representative (any repairs required to be ordered must be instructed by Client Representative). | Inspection to attend and repair - Groundworksslabs around drain and drain have collapsed outside 7 leaze court, caller said that it is dangerous, please make safe. | 2024-06-21 14:37 | Groundworks | Responsive | Andy Young | 28.53 | 28.53 | 5.7 | ESTATE / BLOCK / ROAD
516075 | 449137 | Two Rivers Repairs | R - Routine | 3179 | LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2024-06-14 08:35 | 2024-06-14 09:12 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Attend and repair (Electrical small) consumer unit is coming away from box and door needs replacing | 2024-05-17 12:12 | Electrical | Responsive | Andy Young | 32.45 | 32.45 | 6.49 | ESTATE / BLOCK / ROAD
517673 | 449137 | Two Rivers Repairs | R - Routine | 3179 | LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2024-06-14 10:40 | 2024-06-14 11:25 | CARPENTRY DAYWORKS (where no SOR applicable) | Attend and repair (Electrical small) consumer unit is coming away from box and door needs replacing | 2024-05-17 12:12 | Carpentry | Responsive | Andy Young | 91.4 | 91.4 | 18.28 | ESTATE / BLOCK / ROAD
522234 | 453808 | R.J.CONTRACTING | R - Routine | 3179 | LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2024-08-27 11:06 | 2024-08-27 13:57 | BROKEN GLASS, bits of wood, fridge at front of building next to car park | Dayworks - Routine BROKEN GLASS, bits of wood, fridge at front of building next to car park | 2024-08-27 11:06 |  | Responsive | Andy Young | 176 | 176 | 35.2 | ESTATE / BLOCK / ROAD
522849 | 454254 | R.J.CONTRACTING | R - Routine | 3179 | LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2024-09-06 09:40 | 2024-09-06 09:40 | gas bbq and microwave | Dayworks - Routine gas bbq and microwave | 2024-09-03 15:53 |  | Responsive | Andy Young | 224 | 224 | 44.8 | ESTATE / BLOCK / ROAD
[16 empty] | 552.38 | 110.47
662.85
[15 empty] | each | 30.1295
530921 | 460367 | Two Rivers Repairs | R - Routine | 7763 | FLATS 13 TO 22, LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2025-01-10 15:33 | 2025-01-10 16:46 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. |  | 2024-12-06 10:01 | Walls And Tiles | Responsive | Pete Marks | 29.5 | 29.5 | 5.9 | BLOCK
535769 | 460367 | Two Rivers Repairs | Recall | 7763 | FLATS 13 TO 22, LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2025-02-10 11:35 | 2025-02-10 14:48 | Recall - Flag:Excavate 150mm below required finished level, remove waste and debris, and fill in layers, including compacting 75mm crusher run of broken stone blinding and lay 50mm standard size precast concrete paving flags on 25mm bed of cement mortar (1:4) including point up joints and all cutting and dishing to gullies, covers and the like. |  | 2024-12-06 10:01 | Groundworks | Responsive | Pete Marks | 132.41 | 132.42 | 26.48 | BLOCK
533360 | 460367 | Two Rivers Repairs | R - Routine | 7763 | FLATS 13 TO 22, LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2025-02-07 08:11 | 2025-02-07 14:35 | Step:Form step ne 1000x300x200mm in concrete paving including all necessary excavation, hardcore, extra concrete and all formwork with surfaces trowelled smooth, make good to adjacent finishes and remove waste and debris. | SLABS HHSRS ( SEE NOTES 06/05/2025 ) ISSUES - URGENT STEPS - leading to flat 20 -21 Loose after rtepair with silcone hard set . Attend and repair (WA)Update - Recall 06/05/2025 RECALL ON BOTTOM ROW OF SLABS X 2 LHS LOOSE AND ROCKING AGAIN .- ON COMPLETION LET AREA HOUSING ADVISOR KATH HAMILTON KNOW IT ALL RESOLVED | 2024-12-06 10:01 | Groundworks | Responsive | Pete Marks | 746.8 | 746.8 | 149.36 | BLOCK
[16 empty] | 908.72 | 181.74
1090.46
[15 empty] | each | 109.046
[14 empty] | total recharge for flat 22 |  |  | 139.1755

## manor Court
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
513492 | 447481 | Two Rivers Repairs | R - Routine | 3211 | MANOR COURT, LYDNEY, GLOUCESTERSHIRE | GL15 5BY | 2024-04-18 08:44 | 2024-04-18 08:47 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Attend and repair (Electrical small) security light above the archway no longer working | 2024-04-15 11:27 | Electrical | Responsive | Andy Young | 32.45 | 32.45 | 6.49 | ESTATE / BLOCK / ROAD
513523 | 447498 | REES (ELECTRICAL) & SON | Non Responsive - Routine | 3211 | MANOR COURT, LYDNEY, GLOUCESTERSHIRE | GL15 5BY | 2024-04-26 13:32 | 2024-04-26 13:32 | Dayworks for Rees Electrical main lampost light isnt working | Dayworks for Rees Electrical main lampost light isnt working | 2024-04-15 13:32 |  | Non Responsive | Andy Young | 122 | 122 | 24.4 | ESTATE / BLOCK / ROAD
513782 | 447481 | Two Rivers Repairs | R - Routine | 3211 | MANOR COURT, LYDNEY, GLOUCESTERSHIRE | GL15 5BY | 2024-07-15 07:54 | 2024-07-15 09:41 | External Light:Supply and install in approved location passive infrared detector unit with 1000w lamp, PIR switch, all necessary wiring and control switch and connection to electrical supply, test, set, make good and leave in working order and remove waste and debris. | Attend and repair (Electrical small) security light above the archway no longer working | 2024-04-15 11:27 | Electrical | Responsive | Andy Young | 212.13 | 212.13 | 42.42 | ESTATE / BLOCK / ROAD
[16 empty] | 366.58 | 73.31
439.89
[15 empty] | charge each | 54.9862

## 33 34 oakfields
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
534660 | 463432 | Two Rivers Repairs | R - Routine | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2025-01-28 10:57 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Attend and repair (Electrical small) as you come down the steps the 1st light on the right has had the cover blown off, cover has been left by the light | 2025-01-27 15:26 | Electrical | Responsive | Robert Ward | 26.55 | 26.55 | 5.31 | BLOCK
526913 | 457149 | Two Rivers Repairs | R - Routine | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2024-12-05 08:30 | Wall:Rake out existing joints of brickwork minimum 12mm deep and repoint brickwork in mortar to match existing and remove waste and debris. | Attend and repair (Plumbing small) | 2024-10-16 14:10 | Bricklayers | Responsive | Robert Ward | 296.88 | 296.89 | 59.38 | BLOCK
526735 | 457149 | Two Rivers Repairs | R - Routine | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2024-10-18 13:53 | Client Inspection:Supply and erect ladder for inspection in conjunction with Client Representative to eaves level of roof to property ne 2 storey and remove on completion and remove waste and debris. | Attend and repair (Plumbing small) | 2024-10-16 14:10 | Roofers/chimneys | Responsive | Robert Ward | 371.03 | 371.01 | 74.2 | BLOCK
[15 empty] | 694.45 | 138.89
833.34
[14 empty] | each | 208.335

## 44 oakfields
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
523456 | 454694 | Snape Contracting Ltd | R - Routine | 7739 | FLATS 43 TO 44, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2024-09-10 08:48 | 2024-12-09 13:51 | as per your quote dated 22/07/2024, please proceed with works. | as per your quote dated 22/07/2024, please proceed with works. | 2024-09-10 08:48 | Specialist Works | Responsive | Robert Ward | 0 | 12842.25 | 2568.45 | BLOCK
capped at £250.00

## smithville close
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
531403 | 460792 | Two Rivers Repairs | E - Daytime Emergency | 7800 | FLATS 14A TO 14D, SMITHVILLE CLOSE, ST BRIAVELS, LYDNEY, GLOUCESTERSHIRE | GL15 6TN | 2024-12-12 12:17 | 2024-12-12 13:47 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Tenant's Mum has visited the property while the tenant is away and there is a leak coming through the kitchen and bathroom ceiling. This is coming from the two tanks in the loft, the flooring in the loft is bowing and rotten which might give way. The tenant's Mum is on the way to the property now from Bristol and will arrive by 10:30am. | 2024-12-12 08:43 | Plumbing | Responsive | Pete Marks | 29.5 | 29.5 | 5.9 | BLOCK
531375 | 460770 | Two Rivers Repairs | U - Urgent | 7800 | FLATS 14A TO 14D, SMITHVILLE CLOSE, ST BRIAVELS, LYDNEY, GLOUCESTERSHIRE | GL15 6TN | 2025-01-16 15:08 | 2025-01-16 15:33 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | roof leaking not sure where, into bathroom and kitchen. Attend and repair (roofing small) | 2024-12-11 16:21 | Roofers/chimneys | Responsive | Pete Marks | 29.5 | 29.5 | 5.9 | BLOCK
538783 | 466498 | Two Rivers Repairs | R - Routine | 7800 | FLATS 14A TO 14D, SMITHVILLE CLOSE, ST BRIAVELS, LYDNEY, GLOUCESTERSHIRE | GL15 6TN | 2025-03-24 12:41 | 2025-04-08 13:01 | Client Inspection:Undertake client inspection and testing etc. in connection with fencing and report to Client Representative (any repairs required to be ordered must be instructed by Client Representative). | Please investigate side gate next to 14A and code back works if it needs replacing | 2025-03-20 14:54 | Fencing | Responsive | Pete Marks | 92.35 | 92.35 | 18.46 | BLOCK
531466 | 460792 | Two Rivers Repairs | R - Routine | 7800 | FLATS 14A TO 14D, SMITHVILLE CLOSE, ST BRIAVELS, LYDNEY, GLOUCESTERSHIRE | GL15 6TN | 2025-01-30 08:53 | 2025-01-30 15:56 | Tank:Renew any type of tank with over 113 and ne 227 litres plastic tank, lid, including Byelaw 30 kit, turn water off/on, drain/refill system, adjust and connect pipework, fix new insulation jacket, ballvalve and float and remove old tank, test on completion and remove waste and debris. |  | 2024-12-12 08:43 | Plumbing | Responsive | Pete Marks | 590.3 | 590.28 | 118.07 | BLOCK
[16 empty] | 741.63 | 148.33
889.96
[15 empty] | each | 222.49

## silleys close
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
518462 | 446919 | Axiom Building Solutions Ltd | Z - Asbestos - Routine | 7811 | FLATS 2 TO 3, SILLEYS CLOSE, TUTSHILL, CHEPSTOW, GWENT | NP16 7BP | 2024-07-17 14:14 | 2024-07-17 14:14 | Seal all areas of damaged soffit on stairwell, plywood to areas of possible future damage , silicon edges, two coats of paint & labels.Axiom to supply access equipment, materials, plant, and labour, for the sum of £985.00 Plus VAT. | Seal all areas of damaged soffit on stairwell, plywood to areas of possible future damage , silicon edges, two coats of paint & labels.Axiom to supply access equipment, materials, plant, and labour, for the sum of £985.00 Plus VAT. |  | Asbestos Responsive | Pete Marks | 1024.4 | 1024.4 | 204.88 | BLOCK
capped at £250

## turley court
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
518204 | 450767 | Two Rivers Repairs | R - Routine | 10551 | TURLEY COURT, CINDERFORD, GLOUCESTERSHIRE | GL14 2PE | 2024-06-24 10:34 | 2024-06-24 14:05 | GROUNDWORKS DAYWORKS (where no SOR applicable) | Please locate water leak and rectify as per email sent to Dave Greenwood from Jo Matthews | 2024-06-24 10:11 | Groundworks | Responsive | Andy Young | 88.5 | 88.5 | 17.7 | ESTATE / BLOCK / ROAD
528654 | 458597 | REES (ELECTRICAL) & SON | Non Responsive - Routine | 10551 | TURLEY COURT, CINDERFORD, GLOUCESTERSHIRE | GL14 2PE | 2025-01-22 10:18 | 2025-01-22 16:02 | Rees electrcal - please carry out the service to the external street lighting please | Rees electrcal - please carry out the service to the external street lighting please | 2024-11-11 10:18 |  | Non Responsive | Andy Young | 195 | 195 | 39 | ESTATE / BLOCK / ROAD
530944 | 460388 | R.J.CONTRACTING | R - Routine | 10551 | TURLEY COURT, CINDERFORD, GLOUCESTERSHIRE | GL14 2PE | 2024-12-13 12:35 | 2024-12-13 12:35 | pls clear rubbish and furniture | pls clear rubbish and furniture Dayworks - Routine | 2024-12-06 11:43 |  | Responsive | Andy Young | 494 | 494 | 98.8 | ESTATE / BLOCK / ROAD
[16 empty] | 777.5 | 155.5
933
[15 empty] | each | 93.3

## Tuthill Rise
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
521844 | 424183 | Two Rivers Repairs | R - Routine | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2023-02-24 13:04 | 2024-09-10 11:43 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals.3:Call Schdulers from site to book any follow on. | Attend and repair (Brickwork small) repair of the slabs to the top of the wall surrounding the rear entrance to the flats. | 2023-02-24 13:04 | Bricklayers | Responsive | Pete Marks | 29.5 | 29.5 | 5.9 | BLOCK
538414 | 466242 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-03-17 09:10 | 2025-03-17 09:19 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-03-17 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
536749 | 464974 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-02-24 15:31 | 2025-02-24 15:49 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-02-21 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
534892 | 463599 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-01-30 15:44 | 2025-01-30 16:38 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-01-30 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
532458 | 461675 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-01-06 13:09 | 2025-01-06 13:40 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2025-01-02 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
530998 | 460434 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-12-09 09:40 | 2024-12-09 09:47 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-12-07 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
528922 | 458802 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-11-14 10:37 | 2024-11-14 10:46 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-11-14 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
526919 | 457320 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-10-21 14:10 | 2024-10-21 14:23 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-10-19 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
524732 | 455635 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-09-26 14:35 | 2024-09-26 14:55 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-09-25 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
522166 | 453758 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-09-02 15:55 | 2024-09-02 16:31 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-08-26 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
520407 | 452436 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-08-02 13:15 | 2024-08-02 13:35 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-07-27 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
518734 | 451191 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-07-03 15:54 | 2024-07-03 16:28 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-07-03 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
517313 | 450054 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-06-10 16:05 | 2024-06-10 16:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-06-08 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
515618 | 448804 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-05-15 11:50 | 2024-05-15 12:02 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-05-11 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
513384 | 447398 | Two Rivers Repairs | 7 Days (All Days) | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-04-18 12:30 | 2024-04-18 13:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | 2024-04-14 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
527073 | 457433 | A & E Fire and Security | Planned Maintenance | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2024-09-30 13:55 | 2024-09-30 13:57 | A&E - FRA completed Sept'24 | A&E - FRA completed Sept'24 | 2024-09-30 13:55 |  | Planned Maintenance | Pete Marks | 200 | 200 | 40 | BLOCK
533687 | 462692 | TMS Environmental | Planned Maintenance | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-01-18 14:48 | 2025-01-18 14:48 | TMS following the yearly communal re-inspection it has been identifed the 1st floor ceiling is damaged please can you attend to carry out an encapsulation. | TMS following the yearly communal re-inspection it has been identifed the 1st floor ceiling is damaged please can you attend to carry out an encapsulation. | 2025-01-15 14:48 |  | Planned Maintenance | Pete Marks | 498 | 498 | 99.6 | BLOCK
[16 empty] | 1168.92 | 233.84
1402.76
[15 empty] | each | 233.7933
536061 | 464460 | FireRite | Planned Maintenance | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-06-11 19:53 | 2025-06-11 19:53 | Firerite as per quotation 10289 please can you attend to carry out fire stopping and replacement fire doors £6,871.27 + VAT | Firerite as per quotation 10289 please can you attend to carry out fire stopping and replacement fire doors £6,871.27 + VAT | 2025-02-12 19:53 |  | Planned Maintenance | Pete Marks | 6871.27 | 6871.27 | 1374.25 | BLOCK
capped at $250.00
[13 empty] | recharge for year |  |  | 483.7933

## wyndcliffe house
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
539349 | 466921 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-04-04 14:15 | 2025-04-04 14:33 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2025-03-30 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
537526 | 465551 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-03-06 13:41 | 2025-03-06 14:01 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2025-03-04 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
535701 | 464194 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-02-11 10:45 | 2025-02-11 11:00 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2025-02-08 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
533205 | 462310 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-01-15 11:10 | 2025-01-15 11:30 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2025-01-10 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
531381 | 460775 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-12-17 14:52 | 2024-12-17 15:15 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-12-12 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
529157 | 458957 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-11-19 15:10 | 2024-11-19 15:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-11-16 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
526922 | 457323 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-10-23 12:25 | 2024-10-23 12:37 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-10-19 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
524735 | 455638 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-09-26 15:20 | 2024-09-26 15:44 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-09-25 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
522168 | 453760 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-09-02 10:02 | 2024-09-02 10:13 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-08-26 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
520649 | 452635 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-08-02 10:57 | 2024-08-02 11:16 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-08-01 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
518999 | 451403 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-07-08 13:31 | 2024-07-08 13:37 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-07-06 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
517586 | 450281 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-06-13 15:30 | 2024-06-13 15:38 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-06-13 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
515620 | 448806 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-05-20 14:17 | 2024-05-20 14:35 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-05-11 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
513386 | 447400 | Two Rivers Repairs | 7 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-04-18 09:55 | 2024-04-18 10:30 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | 2024-04-15 | Electrical | Compliance | Pete Marks | 31.53 | 31.53 | 6.31 | BLOCK
526625 | 457103 | Two Rivers Repairs | E - Daytime Emergency | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-10-16 13:33 | 2024-10-16 13:53 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Communal lighting on second floor is not working, requested to be e-job by Leanne in Community Engagement | 2024-10-16 10:11 | Electrical | Responsive | Pete Marks | 58.69 | 58.69 | 11.74 | BLOCK
528662 | 458603 | Hygiene Services | E - Daytime Emergency | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-11-11 10:39 | 2024-11-12 10:05 | end of pathway manhole for flats overflowing | end of pathway manhole for flats overflowing | 2024-11-11 10:39 |  | Responsive | Pete Marks | 80 | 80 | 16 | BLOCK
532296 | 461519 | Two Rivers Repairs | 90 Days (All Days) | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-03-12 14:03 | 2025-03-12 16:44 | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of RCD's and RCBO's, disconnect, repair and renew and make good as necessary after removal of illegal wiring and components and provide report and test certificate in conformity to BS 7671 to the Client Representative and remove waste and debris. (Code C1 and C2 repairs indentified to be undertaken will be ordered separately by the Client's Representative and will be reimbursed at the relevant rates in this Schedule of Rates). | Chepstow - Complete Electrical Installation Condition Report | 2024-12-30 | Electrical | Compliance | Pete Marks | 137.39 | 137.39 | 27.48 | BLOCK
526314 | 456841 | A & E Fire and Security | Planned Maintenance | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-10-11 15:23 | 2024-10-11 15:24 | A&E - retrospective invoice - FRA completed Aug'24 | A&E - retrospective invoice - FRA completed Aug'24 | 2024-10-11 15:23 |  | Planned Maintenance | Pete Marks | 200 | 200 | 40 | BLOCK
527889 | 458058 | Two Rivers Repairs | Z - Asbestos - Planned | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-11-21 14:44 | 2024-11-21 14:44 | To drill 1-5 holes up to 30mm up to 50mm clean and seal following drilling | Can we please raise a job for Lockable sockets to be installed on each floor for the cleaners in the following blocks of flats: | 2024-10-31 13:01 | Asbestos | Asbestos Responsive | Pete Marks | 211 | 211 | 42.2 | BLOCK
529897 | 459587 | R.J.CONTRACTING | R - Routine | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-11-25 12:12 | 2024-12-06 14:27 | table and chairs headboard and general rubbish in black bags | Dayworks - Routine table and chairs headboard and general rubbish in black bags | 2024-11-25 12:12 |  | Responsive | Pete Marks | 190 | 228 | 45.6 | BLOCK
518963 | 451378 | A & E Fire and Security | Planned Maintenance | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-06-07 14:17 | 2024-06-07 14:19 | A&E Retrospective Invoice 460571 - Notice Boards | A&E Retrospective Invoice 460571 - Notice Boards | 2024-06-07 14:17 |  | Planned Maintenance | Pete Marks | 264.94 | 264.94 | 52.99 | BLOCK
520182 | 444506 | Midlands Building & Maintenance Limited | R - Routine | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-02-20 13:14 | 2025-05-02 10:00 | QUOTE TO CLEAN GUTTERS FRONTAND REAR | tenant has emailed and sent photographs of debris fallen from blocked guttering, predominatly moss on the outside shelter, attached email to EDRM for reference Attend and repair (Plumbing small) | 2024-02-20 13:14 | Plumbing | Responsive | Pete Marks | 300 | 300 | 60 | BLOCK
527888 | 458058 | Two Rivers Repairs | R - Routine | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2024-12-17 09:15 | 2025-01-21 13:26 | Power:Isolate supply, provide new 13 amp spur single socket outlet to ground floor, connect to existing ring main with cable run in mini-trunking or rigid PVC conduit chased into wall etc., ne 10.00m, all builders work in connection etc., make all necessary connections, reconnect electricity supply, undertake electrical tests, provide certificate, make good on completion and remove waste and debris. | Can we please raise a job for Lockable sockets to be installed on each floor for the cleaners in the following blocks of flats: | 2024-10-31 13:01 | Electrical | Responsive | Pete Marks | 1162.35 | 1162.35 | 232.47 | BLOCK
[16 empty] | 3083.79 | 616.82
3700.61
[15 empty] | each | 616.7683
536601 | 464865 | Crimewatch Alarms Ltd | Planned Maintenance | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-02-19 11:34 | 2025-04-11 10:38 | Installation og AOV system | Installation of AOV system | 2025-02-19 11:34 |  | Planned Maintenance | Pete Marks | 3558.61 | 3558.61 | 711.72 | BLOCK
capped at £250.00
[15 empty] | total for year | 866.7683

## 1 - 7 wynols
Works Order | Request | Contractor | Priority | Asset Reference | Address | Post Code | Actual Start | Actual Completion | Order Task Description | Request Description | Request Date | Sample Trade | Sample Job Type | Repairs Inspector | Total Charged | Actual Order Value | Actual VAT Value | Asset Type
523378 | 454630 | Two Rivers Repairs | R - Routine | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-09-09 15:18 | 2024-09-09 15:51 | GROUNDWORKS DAYWORKS (where no SOR applicable) | Downpipe outside flat 5 wynols close. Please use wire wool to stop rats getting up the downpipe. Concrete needs to be re done around the gulley. | 2024-09-09 13:05 | Groundworks | Responsive | Robert Ward | 29.5 | 29.5 | 5.9 | BLOCK
538418 | 466246 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2025-03-17 15:46 | 2025-03-17 16:00 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2025-03-17 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
536758 | 464983 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2025-02-24 14:21 | 2025-02-24 14:53 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2025-02-21 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
535001 | 463682 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2025-01-31 12:04 | 2025-01-31 12:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2025-01-31 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
532288 | 461511 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2025-01-07 15:40 | 2025-01-07 16:00 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-12-30 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
530097 | 459758 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-12-06 08:58 | 2024-12-06 09:18 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-11-27 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
528053 | 458176 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-11-04 15:00 | 2024-11-04 15:08 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-11-02 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
525437 | 456175 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-10-09 13:37 | 2024-10-09 13:53 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-10-03 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
523268 | 454534 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-09-10 15:05 | 2024-09-10 15:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-09-08 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
521598 | 453318 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-08-15 09:02 | 2024-08-15 09:21 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-08-15 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
519961 | 452110 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-07-22 14:42 | 2024-07-22 15:36 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-07-20 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
518420 | 450942 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-06-27 11:46 | 2024-06-27 11:57 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-06-27 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
516916 | 449766 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-06-04 09:05 | 2024-06-04 09:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-06-01 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
514523 | 448118 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-05-08 15:53 | 2024-05-08 17:27 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-04-27 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
512275 | 446626 | Two Rivers Repairs | 7 Days (All Days) | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-04-04 12:11 | 2024-04-04 12:31 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Coleford - Monthly alarm test | 2024-03-30 | Electrical | Compliance | Robert Ward | 31.53 | 31.53 | 6.31 | BLOCK
520035 | 452161 | Hygiene Services | U - Urgent | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-07-24 14:12 | 2024-07-24 16:31 | right hand side drain blocked with soil, please report back any findings | Dayworks for Hygiene Servicesright hand side drain blocked with soil, please report back any findings | 2024-07-22 14:12 |  | Responsive | Robert Ward | 70 | 70 | 14 | BLOCK
523647 | 453343 | Amelio | R - Routine | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-09-11 10:53 | 2024-09-16 08:27 | Amelio survey works £1300 | AMELIO - DRAINAGE SURVEY OF BLOCK DUE TO RAT INFESTATION REPORTED BY JO MORRIS AND RJ CONTRACTING | 2024-08-15 10:53 |  | Responsive | Robert Ward | 1300 | 1300 | 260 | BLOCK
524680 | 455596 | Midlands Building & Maintenance Limited | R - Routine | 7745 | FLATS 1 TO 7, WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2024-09-24 10:40 | 2024-10-24 15:13 | MBM - Please carry out flooring works as per Schedule/Quotation Total Cost £2042.04 | Communal Flooring as per quoation recieved - MBM - Total Cost £2042.04 inc.VAT | 2024-09-24 10:40 | Specialist Works | Responsive | Robert Ward | 1701.7 | 1701.7 | 340.34 | BLOCK
3542.62
uable to recharge due to lease