## 1 - 4 Ayland
Works Order | Request | Contractor | Raised | Request Raised By | Sample VAT Code | Confirmation Order | Designated Authoriser | Status | Priority | Total Order Value | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Request Date | Status Date | Sample Trade | Sample Job Type | Actual Order Value | Actual VAT Value | Asset Type
556379 | 480646 | Two Rivers Repairs | 2025-12-04 16:47 | Natalie Wilce | Standard | No | Natalie Wilce | Charged | U - Urgent | 187.82 | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-12-08 09:33 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | As per reception visit, please clear all gutter front and back on this block - this includes the neighbouring properies. Please can you assess the gutter with view to add an additional downpipe. Please report back the potential additional work. Water is coming through the property of 4 Ayland from the gutter, because of the continuous blockage - reported by owner of no 4 | 2025-12-04 16:46 | 2026-01-06 18:53 | Plumbing | Responsive | 187.82 | 37.56 | BLOCK
556321 | 480608 | Two Rivers Repairs | 2025-12-04 07:26 | Shaun Fisher | Standard | No | Shaun Fisher | Charged | R - Routine | 49.67 | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-12-04 09:16 | Gutter:Clean out debris from gutters to any type of property including flush out and test, rod downpipe including clean out gulley and remove debris from site on completion (per elevation). | Clear gutters as per SF | 2025-12-04 07:25 | 2026-01-06 18:53 | Plumbing | Responsive | 49.67 | 9.93 | BLOCK
556320 | 479939 | Two Rivers Repairs | 2025-12-03 16:49 | Lisa Gabb | Standard | No | Emily Morris | Charged | EM - Out of hours | 33.87 | 7785 | FLATS 1 TO 4, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-12-03 16:49 | Plumbing - Out of Hours EmergencyPlumbing - Out of Hours EmergencyPlumbing - Out of Hours Emergency | GUTTER:CLEAN/FLUSH OUT PER ELEVATION | 2025-11-24 10:03 | 2026-01-06 18:53 | Plumbing | Responsive | 33.87 | 6.77 | BLOCK
325.62
[21 empty] | 4 in block | 81.405

## 21 - 32 Ayland
Works Order | Request | Raised | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
564264 | 486722 | 2026-03-16 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-03-16 15:59 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
562261 | 485126 | 2026-02-23 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-02-23 15:58 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
561966 | 484940 | 2026-02-18 11:29 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-02-23 15:14 | Closer to communal door between 22 and 24 is very stiff and heavy when trying to open, please attend to ease 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Closer to communal door between 22 and 24 is very stiff and heavy when trying to open, please attend to ease | 103.98 | 20.8 | BLOCK
560696 | 484031 | 2026-02-03 11:47 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-02-13 14:48 | Closer:Renew or supply and fix heavy duty overhead door closer or other equal and approved screwed to door and frame, make good and remove waste and debris. | As per SW - Could the following works be raised please Location details: External communal door ground floor flats 21 & 32 – off Foley RoadExternal communal door ground floor flats 25 & 27 – off Foley RoadExternal communal door ground floor flats 29 & 31 – off Foley RoadExternal communal door first floor flats 22 & 24 External communal door first floor flats 26 & 28External communal door first floor flats 30 & 32 – NB this is a uPVC door. Work required: Supply and fit new door closer + ease and adjust external timber & glazed doors. X 5 Ease and adjust uPVC door: remove and replace draught excluder x 1 Codes CA390503 X 5 CA325129 1 CA327117 x1 | 512.83 | 102.56 | BLOCK
560481 | 483849 | 2026-02-02 08:01 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-02-02 12:43 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
558014 | 481967 | 2026-01-02 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2026-01-07 15:56 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
556500 | 480740 | 2025-12-08 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-12-09 09:37 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
554725 | 479328 | 2025-11-14 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-11-14 11:48 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
552363 | 477530 | 2025-10-16 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-10-21 10:01 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
550698 | 476156 | 2025-09-22 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-09-23 11:29 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
549059 | 474866 | 2025-08-29 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-08-29 10:57 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
547601 | 473664 | 2025-08-04 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-08-05 14:02 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
545891 | 472381 | 2025-07-04 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-07-09 13:40 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
544225 | 471200 | 2025-06-10 08:01 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-06-11 13:20 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
543871 | 470792 | 2025-06-04 14:40 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-06-23 10:33 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Communal door to flats 22 and 24 is rotting at the step Attend and repair (Carpentry small) | 102.85 | 20.57 | BLOCK
541399 | 468506 | 2025-04-24 08:00 | 7790 | FLATS 21 TO 32, AYLAND CLOSE, NEWENT, GLOUCESTERSHIRE | GL18 1TB | 2025-04-24 14:00 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Newent - Monthly alarm test | 31.53 | 6.31 | BLOCK
1355.51
[9 empty] | 12 in block | 112.9592

## jubilee place
Works Order | Request | Raised | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
564414 | 486861 | 2026-03-17 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-03-17 16:15 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
562275 | 485140 | 2026-02-23 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-02-24 15:32 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
561576 | 484645 | 2026-02-13 09:42 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-02-18 08:36 | Staircase:Refix any loose tread by screwing through tread into top edge of riser (where there is no access to underside of staircase). | Stairs leading to Flats 26 & 28 - capping to the stairs risers from the 5th step to the top step are loose - please refix. | 60.48 | 12.1 | BLOCK
560349 | 483772 | 2026-01-30 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-02-02 14:52 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
559151 | 482896 | 2026-01-15 15:08 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-01-22 11:44 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Reported by no 31 that the communal light outside no 29 is not working | 44.25 | 8.85 | BLOCK
558022 | 481975 | 2026-01-05 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2026-01-06 11:25 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
556212 | 480548 | 2025-12-03 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-12-10 16:27 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
554291 | 479005 | 2025-11-10 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-11-10 16:26 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
552265 | 477456 | 2025-10-15 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-10-17 09:46 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
548975 | 474821 | 2025-08-28 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-09-22 09:14 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
547608 | 473671 | 2025-08-04 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-08-04 15:44 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
546012 | 472468 | 2025-07-07 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-07-10 13:29 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
544962 | 471732 | 2025-06-19 15:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-07-17 09:58 | Client Inspection:Undertake client inspection and testing etc. in connection with fencing and report to Client Representative (any repairs required to be ordered must be instructed by Client Representative). | Inspection to attend and repair - Fencing and gates broken fence post in gardens of 25-28 Jubilee Place | 65.26 | 13.05 | BLOCK
544252 | 471225 | 2025-06-10 08:02 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-06-12 11:14 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
542072 | 469026 | 2025-05-05 08:01 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-05-09 13:11 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
541610 | 468668 | 2025-04-28 08:55 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-04-29 11:15 | Sofa and other bits of rubbish has been dumped outside the block of flats | Sofa and other bits of rubbish has been dumped outside the block of flats | 98 | 19.6 | BLOCK
540146 | 467508 | 2025-04-10 08:00 | 7802 | FLATS 25 TO 32, JUBILEE PLACE, STAUNTON, GLOUCESTER, GLOUCESTERSHIRE | GL19 3RS | 2025-04-10 13:45 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Gloucester - Monthly alarm test | 31.53 | 6.31 | BLOCK
813.51
[9 empty] | 8 in block | 101.6887

## Harrison Way
Works Order | Request | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Sample Trade | Sample Job Type | Actual Order Value | Actual VAT Value | Asset Type
565217 | 487438 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2026-03-27 13:44 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
562881 | 485573 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2026-03-03 16:31 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
560988 | 484223 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2026-02-06 16:27 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
558522 | 482408 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2026-01-13 12:22 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
557076 | 481187 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-12-16 16:32 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
555348 | 479830 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-11-21 16:24 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
552260 | 477451 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-10-28 17:04 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 261.63 | 52.33 | BLOCK
550697 | 476155 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-09-22 15:52 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
548967 | 474813 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-08-29 16:08 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
547397 | 473506 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-08-04 09:43 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
545890 | 472380 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-07-07 16:29 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
544214 | 471189 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-06-10 11:42 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
542064 | 469018 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-05-07 12:18 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
540142 | 467504 | 7759 | FLATS & SHOPS 30 TO 32, HARRISON WAY, LYDNEY, GLOUCESTERSHIRE | GL15 5BN | 2025-04-10 15:02 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
805.88
[10 empty] | 3 in block | 268.6267

## Leaze Court
Works Order | Request | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
542217 | 469158 | 7763 | FLATS 13 TO 22, LEAZE COURT, MOUNT PLEASANT, LYDNEY, GLOUCESTERSHIRE | GL15 5QP | 2025-05-16 17:00 | SLABS STEPS LEADING UP TO PLATFORM TO FLAT20- 21 HHSRS BOTTOM ROW OF STEPS -FDL Carry out the following woirks as per your quotation - Carefully lift the loose x 2 slabs to LHS of the bottom row with damaging teh surrounding slabs -removal all old bedding motar dirt etc - prep clean the stair base to ensure suitablle bonding surface - check the underlying substrate for stability and repair any minor defects as nec prep a strong /durable bedding motar /fastset apply to stair base ensuring full coverage to suit - follow on to relay the slabs in their orginal postion -point all joints witha suitable jointing compound - ( allow the bedding to cure as per the manufacturers detail .before allowing foot traffic ) slabs to be left soild underfoot level and flush with the surround slabs - works to comence at 7am on 08/05/2025 as per your quotation | SLABS STEPS LEADING UP TO PLATFORM TO FLATS 20- 21 HHSRS URGENT WORKS TO LOOSE /ROCKING BOTTOM ROW OF STEPS -FDL Carry out the following woirks as per your quotation - Carefully lift the loose x 2 slabs to LHS of the bottom row with damaging teh surrounding slabs -removal all old bedding motar dirt etc - prep clean the stair base to ensure suitablle bonding surface - check the underlying substrate for stability and repair any minor defects as nec prep a strong /durable bedding motar /fastset apply to stair base ensuring full coverage to suit - follow on to relay the slabs in their orginal postion -point all joints witha suitable jointing compound - ( allow the bedding to cure as per the manufacturers detail .before allowing foot traffic ) slabs to be left soild underfoot level and flush with the surround slabs - works to comence at 7am on 08/05/2025 as per your quotation | 60 | 12 | BLOCK
72
[8 empty] | 10 in block | 7.2

## 33 34 Oakfields
Works Order | Request | Contractor | Raised | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Sample Trade | Sample Job Type | Actual Order Value | Actual VAT Value | Asset Type
552871 | 477943 | Two Rivers Repairs | 2025-10-22 08:04 | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2025-12-17 10:38 | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of RCD's and RCBO's, disconnect, repair and renew and make good as necessary after removal of illegal wiring and components and provide report and test certificate in conformity to BS 7671 to the Client Representative and remove waste and debris. (Code C1 and C2 repairs indentified to be undertaken will be ordered separately by the Client's Representative and will be reimbursed at the relevant rates in this Schedule of Rates). | Coleford - Complete Electrical Installation Condition Report | Electrical | Compliance | 137.39 | 27.48 | BLOCK
545464 | 472092 | Two Rivers Repairs | 2025-06-26 13:51 | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2025-06-27 16:22 | Client Inspection:Undertake client inspection and testing etc. in connection with fencing and report to Client Representative (any repairs required to be ordered must be instructed by Client Representative). | Inspection to attend and repair - Fencing and gates Rotten post needs replacing. 33a-34b oakfields | Fencing | Responsive | 32.39 | 6.47 | BLOCK
541981 | 468937 | Two Rivers Repairs | 2025-05-01 14:18 | 7738 | FLATS 33 TO 34, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2025-05-01 15:23 | As per residents email - we’ve communal lights full of water and not working - please report any further work back 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | As per residents email - we’ve communal lights full of water and not working - please report any further work back | Electrical | Responsive | 24.63 | 4.93 | BLOCK
233.29
[12 empty] | 4 in block | 58.3225

## 43 44 Oakfields
Works Order | Request | Contractor | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Customer Services Advisor | Actual Order Value | Actual VAT Value | Asset Type
549855 | 475513 | Davies Carpentry & Fire Protection Ltd | 7739 | FLATS 43 TO 44, OAKFIELDS, COLEFORD, GLOUCESTERSHIRE | GL16 8EN | 2025-10-22 11:04 | Quote Reference: DCFP/Q109 £1,800.80Remove existing double door set and fan light and build a new external grade fire rated stud to house a single door.Install a FD30S external grade single Fire Door.Supply and fit a new fiberglass electric meter cupboard door.Fire Door Including:• 1 x door sets • Paint finished• Hardwood Threshold • Euro mortice dead lock with thumb turn and finger pull• Fire stopping from substrate to back of frame• Detailed evidence of the installation including photos• PVC architraves/trims • Disposal of existing door.• Firas certification. | Quote Reference: DCFP/Q109 £1,800.80Remove existing double door set and fan light and build a new external grade fire rated stud to house a single door.Install a FD30S external grade single Fire Door.Supply and fit a new fiberglass electric meter cupboard door.Fire Door Including:• 1 x door sets • Paint finished• Hardwood Threshold • Euro mortice dead lock with thumb turn and finger pull• Fire stopping from substrate to back of frame• Detailed evidence of the installation including photos• PVC architraves/trims • Disposal of existing door.• Firas certification. | Not Required | 1800.8 | 360.16 | BLOCK
2160.96
[10 empty] | 4 in block | 540.24 | no S20 capped at £250

## 2 - 5 St Marys
Works Order | Request | Contractor | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
562658 | 485439 | Two Rivers Repairs | 7771 | FLATS 2 TO 5, ST. MARYS SQUARE, LYDNEY, GLOUCESTERSHIRE | GL15 5AL | 2026-02-26 16:35 | Light Fitting:Isolate supply, disconnect, clear away and renew bulkhead light fitting with metal alloy clad body, polycarbonate diffuser with screw fitting and 28 watt 2D lamp, connect to existing cables, reconnect electricity supply, undertake electrical tests and make good on completion and remove waste and debris. | As per LP - Can a job be raised to repair light in communal area of the above address please. 1x 856611 | 86.42 | 17.28 | BLOCK
541982 | 468938 | Davies Carpentry & Fire Protection Ltd | 7771 | FLATS 2 TO 5, ST. MARYS SQUARE, LYDNEY, GLOUCESTERSHIRE | GL15 5AL | 2026-03-29 15:54 | Check compartmentation in Roof Void | Check compartmentation in Roof VoidDavies SOR 1/2 day £250 | 250 | 50 | BLOCK
540435 | 467797 | Two Rivers Repairs | 7771 | FLATS 2 TO 5, ST. MARYS SQUARE, LYDNEY, GLOUCESTERSHIRE | GL15 5AL | 2025-06-03 16:29 | Test:Carry out test of domestic installation to occupied property complete comprising continuity, insulation resistance, polarity, earth fault loop impedance and operation of RCD's and RCBO's, disconnect, repair and renew and make good as necessary after removal of illegal wiring and components and provide report and test certificate in conformity to BS 7671 to the Client Representative and remove waste and debris. (Code C1 and C2 repairs indentified to be undertaken will be ordered separately by the Client's Representative and will be reimbursed at the relevant rates in this Schedule of Rates). | Lydney - Complete Electrical Installation Condition Report | 137.39 | 27.48 | BLOCK
568.57
[9 empty] | 4 in block | 142.1425

## 14-17 St Marys
Works Order | Request | Contractor | Raised | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
541988 | 468943 | Davies Carpentry & Fire Protection Ltd | 2025-05-01 14:37 | FLATS 14 TO 17, ST. MARYS SQUARE, LYDNEY, GLOUCESTERSHIRE | GL15 5AL | 2025-10-22 14:35 | Upgrade store cupboard to FD30s , install CSS | Upgrade store cupboard to FD30s , install CSS Davies quote QF2094 - qty 6 doors | 8325.6 | 1665.12 | BLOCK
9990.72
[9 empty] | 4 in block | 2497.68 | capped at £250, no section 20

## Tuthill Rise
Works Order | Request | Contractor | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Sample Trade | Sample Job Type | Actual Order Value | Actual VAT Value | Asset Type
564263 | 486721 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-03-16 15:06 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
562260 | 485125 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-02-23 14:47 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
560240 | 483683 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-02-02 12:12 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
557783 | 481713 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-01-05 14:26 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
556205 | 480541 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-12-03 13:10 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
555635 | 480072 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-12-10 14:48 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Attend and repair (Plumbing small) | Plumbing | Responsive | 88.5 | 17.7 | BLOCK
554283 | 478997 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-10 13:32 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
553979 | 478636 | LEL Scaffolding | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-24 10:47 | Scaffolding H05 | A repair is required at this property. Guttering to RHS elevation as viewed from Naas Lane is leaking. Water is flooding into communal walkway, access to ground floor flats, water is also causing damage to the brick course directly below. | Scaffolding | Responsive | 480 | 96 | BLOCK
553977 | 478636 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-28 11:50 | Gutter:Renew ne 112mm PVCu gutter union or fitting rubbers of any profile including remake joints and line and level and remove waste and debris. | A repair is required at this property. Guttering to RHS elevation as viewed from Naas Lane is leaking. Water is flooding into communal walkway, access to ground floor flats, water is also causing damage to the brick course directly below. | Plumbing | Responsive | 68.2 | 13.64 | BLOCK
553918 | 478637 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-02-04 08:37 | Walls and Ceilings:Prepare and apply one mist coat and two full coats of emulsion paint to walls or ceilings in patch repairs to match existing including all joints to adjacent surfaces and finishes. | A repair is required at this property. PVC panel of top floor landing window, adajcent to the bin stores of Flats 5 & 6 has blown and wooden skirting is rotten. This is a potential H&S risk. Externally the wooden base rail is rotten. Please make safe or cordon off until repair/replacement carried out. | Painting | Responsive | 58.01 | 11.6 | BLOCK
553917 | 478637 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2026-02-11 09:02 | Fascia/Barge:Renew fascia or bargeboard with proprietary PVCu board ne 300mm wide fixed to roof timbers, remove and refix rainwater goods and any cabling, remove existing board, adjust roof tiles and felt, renewal of any support battens and all joints, including all cutting and packing to ensure line and level and remove waste and debris. | A repair is required at this property. PVC panel of top floor landing window, adajcent to the bin stores of Flats 5 & 6 has blown and wooden skirting is rotten. This is a potential H&S risk. Externally the wooden base rail is rotten. Please make safe or cordon off until repair/replacement carried out. | Carpentry | Responsive | 967.48 | 193.5 | BLOCK
553802 | 478637 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-03 15:05 | PVC panel of top floor landing window, adajcent to the bin stores of Flats 5 & 6 has blown and wooden skirting is rotten. This is a potential H&S risk. Externally the wooden base rail is rotten. Please make safe or cordon off until repair/replacement carried out. 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | A repair is required at this property. PVC panel of top floor landing window, adajcent to the bin stores of Flats 5 & 6 has blown and wooden skirting is rotten. This is a potential H&S risk. Externally the wooden base rail is rotten. Please make safe or cordon off until repair/replacement carried out. | Carpentry | Responsive | 88.5 | 17.7 | BLOCK
553801 | 478636 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-04 13:39 | Guttering to RHS elevation as viewed from Naas Lane is leaking. Water is flooding into communal walkway, access to ground floor flats, water is also causing damage to the brick course directly below. 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | A repair is required at this property. Guttering to RHS elevation as viewed from Naas Lane is leaking. Water is flooding into communal walkway, access to ground floor flats, water is also causing damage to the brick course directly below. | Plumbing | Responsive | 105.17 | 21.03 | BLOCK
553799 | 478634 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-11-03 14:19 | 1:Attend and repair; complete works as necessary. 2:SOR to be varied upon completion to reflect actuals. 3:Call Schedulers from site to book any follow on. | Loose handraile between flats 5 and 6 Attend and repair (Carpentry small) | Carpentry | Responsive | 118 | 23.6 | BLOCK
552259 | 477450 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-10-16 16:26 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
550696 | 476154 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-09-22 16:28 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
548965 | 474811 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-08-29 15:56 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
547390 | 473499 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-08-04 09:23 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
545883 | 472373 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-07-07 15:46 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
544207 | 471182 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-06-10 12:03 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
542768 | 469519 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-05-14 17:28 | PLUMBING DAYWORKS (where no SOR applicable)Jason has called to report there is a leak in the block, the opperatives on site carrying out FRA works have noticed it but cannot see where the leak is coming from. They have advised they are working on the 1st floor in the block and when the water is dripping from the ceiling above they have pencil marked around the water marks where it is dripping on the floor for the opperative to see. Opperative carrying out FRA is called Harvey & happy for you to call him 07904231364 | Jason has called to report there is a leak in the block, the opperatives on site carrying out FRA works have noticed it but cannot see where the leak is coming from. They have advised they are working on the 1st floor in the block and when the water is dripping from the ceiling above they have pencil marked around the water marks where it is dripping on the floor for the opperative to see. Opperative carrying out FRA is called Harvey & happy for you to call him 07904231364 | Plumbing | Responsive | 29.5 | 5.9 | BLOCK
542063 | 469017 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-05-14 12:09 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
541810 | 464460 | TMS Environmental | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-05-06 19:53 | TMS Please remove the asbestos from the corner outside of flat 6. Photo attached. | Firerite as per quotation 10289 please can you attend to carry out fire stopping and replacement fire doors £6,871.27 + VAT |  | Planned Maintenance | 530 | 106 | BLOCK
540141 | 467503 | Two Rivers Repairs | 7776 | FLATS 1 TO 6, TUTHILL RISE, LYDNEY, GLOUCESTERSHIRE | GL15 5BP | 2025-04-11 13:15 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Lydney - Monthly alarm test | Electrical | Compliance | 31.53 | 6.31 | BLOCK
3569.79
[11 empty] | 6 in block | 594.965

## Turley Court
Works Order | Request | Contractor | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Actual Order Value | Actual VAT Value | Asset Type
560017 | 483521 | REES (ELECTRICAL) & SON | 10551 | TURLEY COURT, CINDERFORD, GLOUCESTERSHIRE | GL14 2PE | 2026-01-27 09:44 | Rees electrcal - please carry out the service to the external communal lighting please | 264 | 52.8 | ESTATE / BLOCK / ROAD
316.8
[8 empty] | 10 in block | 31.68

## Wyndecliffe
Works Order | Request | Contractor | Raised | Request Raised By | Sample VAT Code | Confirmation Order | Designated Authoriser | Status | Total Order Value | Asset Reference | Address | Post Code | Actual Completion | Order Task Description | Request Description | Sample Trade | Sample Job Type | Total Charged | Initial Raised Value | Final Raised Value | Contact Name | Total Cost | Total Posted | Initial Raised Cancellations | Final Raised Cancellations | Original Order Value | Final Order Value | Repairs Status | Cost Centre | Repairs Cycle | Housing Officer | Customer Services Advisor | Actual Order Value | Actual VAT Value | Asset Type
565314 | 487518 | Two Rivers Repairs | 2026-03-30 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2026-03-30 11:43 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
563517 | 485569 | Two Rivers Repairs | 2026-03-04 09:41 | Sarah Craggs | Standard | No | Aimee Hughes | Charged | 8.89 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2026-03-12 08:38 | Lamp:Take off, clear away and renew 8 watt fluorescent lamp to bulkhead fitting including remove and refix cover and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Responsive | 8.89 | 8.89 | 8.89 |  | 0 | 0 | 0 | 0 | 8.89 | 0 | Normal |  |  | Anita Mills | Not Required | 8.89 | 1.78 | BLOCK
562877 | 485569 | Two Rivers Repairs | 2026-03-02 08:01 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2026-03-04 08:30 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
561126 | 484321 | Two Rivers Repairs | 2026-02-09 08:01 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2026-02-09 11:13 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
558621 | 482489 | Two Rivers Repairs | 2026-01-12 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2026-01-14 10:18 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
557072 | 481183 | Two Rivers Repairs | 2025-12-15 08:01 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-12-19 15:41 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
555223 | 479743 | Two Rivers Repairs | 2025-11-20 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-11-21 10:44 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
553221 | 478228 | Two Rivers Repairs | 2025-10-27 06:07 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-10-27 15:22 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
551306 | 476678 | Two Rivers Repairs | 2025-10-01 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-10-02 11:38 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
549236 | 475020 | Two Rivers Repairs | 2025-09-02 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-09-08 15:14 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
547393 | 473502 | Two Rivers Repairs | 2025-07-31 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-08-06 14:30 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
545886 | 472376 | Two Rivers Repairs | 2025-07-04 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-07-07 12:09 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
544210 | 471185 | Two Rivers Repairs | 2025-06-10 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-06-11 15:23 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
541588 | 468645 | Two Rivers Repairs | 2025-04-28 08:00 | Sarah Craggs | Standard | No | Sarah Craggs | Charged | 31.53 | 7804 | WYNDCLIFFE HOUSE, BUTTINGTON ROAD, SEDBURY, CHEPSTOW, GWENT | NP16 7AN | 2025-04-29 10:57 | Emergency Lighting:Attend and carry out service to emergency lighting installation complete to block of dwellings or scheme, including provision of minor parts as necessary, test and leave in working order and remove waste and debris. | Chepstow - Monthly alarm test | Electrical | Compliance | 31.53 | 31.53 | 31.53 |  | 0 | 0 | 0 | 0 | 31.53 | 0 | Normal |  |  | Anita Mills | Not Required | 31.53 | 6.31 | BLOCK
502.59
[33 empty] | 6 in block | 83.765

## Wynols Close
Works Order | Request | Contractor | Address | Post Code | Actual Completion | Order Task Description | Request Description | Actual Order Value | Actual VAT Value | Asset Type
565168 | 487402 | TrunkArb Tree Surgery Ltd | WYNOLS CLOSE, BROADWELL, COLEFORD, GLOUCESTERSHIRE | GL16 7RR | 2026-04-16 12:05 | T678 - ash; fell - list says removetreat/grind stump | T683 - Ash; stumpgrind/treat | 190 | 38 | ESTATE / BLOCK / ROAD
228